## Project Plan Updated
JIFFY POS PROJECT DETAILED WORK PLAN
WBS | Task Name | Resource Names | % Complete | % Work Complete | Status | Duration | Start | Finish | Actual Start | Actual Finish | Remark
0 | RM-Retail POS Project Detailed Work Plan |  | 16.97% | 16.87% | Late | 364 days | 2026-05-11 | 2027-09-30 | 2026-05-11
1 | Milestone1 - System Scope (20%) | RM,VTEC | 66.23% | 66.1% | Late | 125 days | 2026-05-11 | 2026-10-30 | 2026-05-11
1.1 | Project Mobilization | RM,VTEC | 100% | 100% | Complete | 30 days | 2026-05-11 | 2026-06-19 | 2026-05-11 | 2026-06-19
1.1.1 | Kickoff Preparation | VTEC | 100% | 100% | Complete | 5 days | 2026-05-11 | 2026-05-15 | 2026-05-11 | 2026-05-15
1.1.2 | Project Team Organization | RM,VTEC | 100% | 100% | Complete | 5 days | 2026-05-11 | 2026-05-15 | 2026-05-11 | 2026-05-15
1.1.3 | Governance Setup | RM,VTEC | 100% | 100% | Complete | 5 days | 2026-05-11 | 2026-05-15 | 2026-05-11 | 2026-05-15
1.1.4 | Communication Setup | RM,VTEC | 100% | 100% | Complete | 5 days | 2026-05-11 | 2026-05-15 | 2026-05-11 | 2026-05-15
1.1.5 | Detailed Work Plan | RM,VTEC | 100% | 100% | Complete | 5 days | 2026-06-08 | 2026-06-12 | 2026-06-08 | 2026-06-12
1.1.6 | Kickoff Meeting | RM,VTEC | 100% | 100% | Complete | 1 days | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-16
1.1.7 | Mobilization Confirmed & Completed | RM | 100% | 100% | Complete | 3 days | 2026-06-17 | 2026-06-19 | 2026-06-17 | 2026-06-19
1.2 | The procurement and commercial process | PTTRM,VTEC | 97.86% | 97.86% | On Schedule | 53 days | 2026-07-20 | 2026-09-30 | 2026-07-20
1.2.1 | Hardware | PTTRM,VTEC | 95.71% | 95.71% | On Schedule | 85 days | 2026-07-20 | 2026-11-15 | 2026-07-20
1.2.1.1 | Prepare HW Proposal for 150 Sites | VTEC | 100% | 100% | Complete | 10 days | 2026-07-20 | 2026-07-31 | 2026-07-20 | 2026-07-31
1.2.1.2 | Proposal Review & Approval | PTTRM | 100% | 100% | Complete | 19 days | 2026-08-04 | 2026-08-28 | 2026-08-04 | 2026-08-28
1.2.1.3 | Draft TOR | PTTRM | 100% | 100% | Complete | 5 days | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04
1.2.1.4 | TOR Review & Confirmation | PTTRM / VTEC | 100% | 100% | Complete | 5 days | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04
1.2.1.5 | Issue Final TOR | PTTRM | 100% | 100% | Complete | 5 days | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-11
1.2.1.6 | Contract Preparation & Execution | PTTRM / VTEC | 100% | 100% | Complete | 5 days | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18
1.2.1.7 | PO Processing / PO Issuance | PTTRM | 70% | 70% | On Schedule | 40 days | 2026-09-21 | 2026-11-15 | 2026-09-21
1.2.2 | Software + Support + Cloud | PTTRM,VTEC | 100% | 100% | Complete | 50 days | 2026-07-20 | 2026-09-25 | 2026-07-20 | 2026-09-25
1.2.2.1 | Prepare Software + Support + Cloud Proposal for 150 Sites | VTEC | 100% | 100% | Complete | 10 days | 2026-07-20 | 2026-07-31 | 2026-07-20 | 2026-07-31
1.2.2.2 | Proposal Review & Approval | PTTRM | 100% | 100% | Complete | 19 days | 2026-08-04 | 2026-08-28 | 2026-08-04 | 2026-08-28
1.2.2.3 | Draft TOR | PTTRM | 100% | 100% | Complete | 5 days | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04
1.2.2.4 | TOR Review & Confirmation | PTTRM / VTEC | 100% | 100% | Complete | 5 days | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04
1.2.2.5 | Issue Final TOR | PTTRM | 100% | 100% | Complete | 5 days | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-11
1.2.2.6 | Contract Preparation & Execution | PTTRM / VTEC | 100% | 100% | Complete | 5 days | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18
1.2.2.7 | PO Processing / PO Issuance | PTTRM | 100% | 100% | Complete | 5 days | 2026-09-21 | 2026-09-25 | 2026-09-21 | 2026-09-25
1.3 | Cloud Infrastructure Design | AWS,RM,VTEC | 100% | 100% | Complete | 15 days | 2026-06-29 | 2026-07-17 | 2026-06-29 | 2026-07-17
1.3.1 | Infrastructure Requirement Alignment | AWS,RM,VTEC | 100% | 100% | Complete | 5 days | 2026-06-29 | 2026-07-03 | 2026-06-29 | 2026-07-03
1.3.2 | Infrastructure Sizing Confirmation | AWS,RM,VTEC | 100% | 100% | Complete | 5 days | 2026-06-29 | 2026-07-03 | 2026-06-29 | 2026-07-03
1.3.3 | Cloud Architecture & Environment Design | AWS,RM,VTEC | 100% | 100% | Complete | 5 days | 2026-07-06 | 2026-07-10 | 2026-07-06 | 2026-07-10
1.3.4 | Review and Confirm Design | RM | 100% | 100% | Complete | 5 days | 2026-07-13 | 2026-07-17 | 2026-07-13 | 2026-07-17
1.4 | Requirement & Design | RM,VTEC | 97.81% | 97.69% | Late | 73 days | 2026-06-22 | 2026-09-30 | 2026-06-22
1.4.1 | BA01 - โครงสร้างข้อมูลหลัก (Key Data Structure) | RM,VTEC | 100% | 100% | Complete | 50 days | 2026-06-22 | 2026-08-28 | 2026-06-22 | 2026-08-28
1.4.1.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.1.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 38 days | 2026-07-01 | 2026-08-21 | 2026-07-01 | 2026-08-21
1.4.1.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-24 | 2026-08-28 | 2026-08-24 | 2026-08-28
1.4.1.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-08-31 | 2026-09-02 | 2026-08-31 | 2026-09-02
1.4.1.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.2 | BA02 - การจัดการส่วนกลางและรายงาน (HQ & Reporting) | RM,VTEC | 100% | 100% | Complete | 64 days | 2026-06-22 | 2026-09-17 | 2026-06-22 | 2026-09-17
1.4.2.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.2.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 46 days | 2026-07-01 | 2026-09-02 | 2026-07-01 | 2026-09-02
1.4.2.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-09-03 | 2026-09-09 | 2026-09-03 | 2026-09-09
1.4.2.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-09-10 | 2026-09-14 | 2026-09-10 | 2026-09-14
1.4.2.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-15 | 2026-09-17 | 2026-09-15 | 2026-09-17
1.4.3 | BA03 - ระบบสมาชิกและโปรโมชั่น (CRM & Promotion Management) | RM,VTEC | 100% | 100% | Complete | 50 days | 2026-06-22 | 2026-08-28 | 2026-06-22 | 2026-08-28
1.4.3.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.3.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 38 days | 2026-07-01 | 2026-08-21 | 2026-07-01 | 2026-08-21
1.4.3.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-24 | 2026-08-28 | 2026-08-24 | 2026-08-28
1.4.3.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-08-31 | 2026-09-02 | 2026-08-31 | 2026-09-02
1.4.3.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.4 | BA04 - การชำระเงินและการเชื่อมต่อ Blueplus+ (Payment & Blueplus+) | RM,VTEC | 100% | 100% | Complete | 50 days | 2026-06-22 | 2026-08-28 | 2026-06-22 | 2026-08-28
1.4.4.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.4.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 38 days | 2026-07-01 | 2026-08-21 | 2026-07-01 | 2026-08-21
1.4.4.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-24 | 2026-08-28 | 2026-08-24 | 2026-08-28
1.4.4.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-08-31 | 2026-09-02 | 2026-08-31 | 2026-09-02
1.4.4.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.5 | BA-05 - การปฏิบัติงานของสาขาและหน้าร้าน (Store & Front Operation) | RM,VTEC | 100% | 100% | Complete | 59 days | 2026-06-22 | 2026-09-10 | 2026-06-22 | 2026-09-10
1.4.5.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.5.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 41 days | 2026-07-01 | 2026-08-26 | 2026-07-01 | 2026-08-26
1.4.5.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-27 | 2026-09-02 | 2026-08-27 | 2026-09-02
1.4.5.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.5.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-08 | 2026-09-10 | 2026-09-08 | 2026-09-10
1.4.6 | BA-06 - การปฏิบัติงานหลังร้านและการจัดการสินค้าคงคลัง (Store Back Operation & Inventory Management) | RM,VTEC | 100% | 100% | Complete | 59 days | 2026-06-22 | 2026-09-10 | 2026-06-22 | 2026-09-10
1.4.6.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.6.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 41 days | 2026-07-01 | 2026-08-26 | 2026-07-01 | 2026-08-26
1.4.6.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-27 | 2026-09-02 | 2026-08-27 | 2026-09-02
1.4.6.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.6.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-08 | 2026-09-10 | 2026-09-08 | 2026-09-10
1.4.7 | BA-07 - กระบวนการสั่งซื้อสินค้าจากสาขาสู่ส่วนกลาง (Branch Ordering & HQ Procurement Integration) | RM,VTEC | 100% | 100% | Complete | 59 days | 2026-06-22 | 2026-09-10 | 2026-06-22 | 2026-09-10
1.4.7.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.7.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 41 days | 2026-07-01 | 2026-08-26 | 2026-07-01 | 2026-08-26
1.4.7.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-27 | 2026-09-02 | 2026-08-27 | 2026-09-02
1.4.7.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.7.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-08 | 2026-09-10 | 2026-09-08 | 2026-09-10
1.4.8 | BA-08 – การเชื่อมต่อ E-Tax ผ่าน IES (E-Tax Integration via IES) | RM,VTEC | 100% | 100% | Complete | 50 days | 2026-06-22 | 2026-08-28 | 2026-06-22 | 2026-08-28
1.4.8.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.8.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 38 days | 2026-07-01 | 2026-08-21 | 2026-07-01 | 2026-08-21
1.4.8.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-08-24 | 2026-08-28 | 2026-08-24 | 2026-08-28
1.4.8.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-08-31 | 2026-09-02 | 2026-08-31 | 2026-09-02
1.4.8.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-03 | 2026-09-07 | 2026-09-03 | 2026-09-07
1.4.9 | BA-09 – การจัดเตรียมข้อมูลสำหรับการใช้งาน (Data View & Data Preparation) | RM,VTEC | 100% | 100% | Complete | 64 days | 2026-06-22 | 2026-09-17 | 2026-06-22 | 2026-09-17
1.4.9.1 | Get Requirement | VTEC | 100% | 100% | Complete | 22 days | 2026-06-22 | 2026-07-21 | 2026-06-22 | 2026-07-21
1.4.9.2 | DSD Preparation | VTEC | 100% | 100% | Complete | 46 days | 2026-07-01 | 2026-09-02 | 2026-07-01 | 2026-09-02
1.4.9.3 | DSD Review | RM | 100% | 100% | Complete | 5 days | 2026-09-03 | 2026-09-09 | 2026-09-03 | 2026-09-09
1.4.9.4 | DSD Revise | VTEC | 100% | 100% | Complete | 3 days | 2026-09-10 | 2026-09-14 | 2026-09-10 | 2026-09-14
1.4.9.5 | DSD Finalization | RM | 100% | 100% | Complete | 3 days | 2026-09-15 | 2026-09-17 | 2026-09-15 | 2026-09-17
1.4.10 | DSD Consolidation & Sign-off | RM,VTEC | 82.5% | 81.5% | Late | 9 days | 2026-09-15 | 2026-09-25 | 2026-09-15
1.4.10.1 | Sign-off Preparation | VTEC | 100% | 100% | Complete | 4 days | 2026-09-15 | 2026-09-18 | 2026-09-15 | 2026-09-18
1.4.10.2 | Sign-off | RM | 65% | 63% | Late | 30 days | 2026-09-21 | 2026-10-30 | 2026-09-21
1.5 | Technical Specification Document | RM,VTEC | 33.33% | 32.83% | Late | 40 days | 2026-09-07 | 2026-10-30 | 2026-09-07
1.5.1 | Preparation | VTEC | 100% | 100% | Complete | 5 days | 2026-09-07 | 2026-09-11 | 2026-09-07 | 2026-09-11
1.5.2 | Review | RM | 100% | 97% | Late | 25 days | 2026-09-14 | 2026-10-16 | 2026-09-14
1.5.3 | Revise | VTEC | 0% | 0% | Not Started | 3 days | 2026-10-19 | 2026-10-21
1.5.4 | Finalization | RM | 0% | 0% | Not Started | 2 days | 2026-10-22 | 2026-10-23
1.5.5 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 1 days | 2026-10-26 | 2026-10-26
1.5.6 | Sign-off | RM | 0% | 0% | Not Started | 4 days | 2026-10-27 | 2026-10-30
2 | Milestone2 - Implementation (20%) | AWS,RM,VTEC | 1.66% | 1.381% | Late | 135 days | 2026-09-14 | 2027-03-19 | 2026-09-14
2.1 | QAS Environment Preparation | AWS,RM,VTEC | 13.89% | 11.33% | Late | 10 days | 2026-09-14 | 2026-09-25 | 2026-09-14
2.1.1 | QAS Environment Setup (Could + POS) | AWS,RM,VTEC | 41.67% | 34% | Late | 10 days | 2026-10-12 | 2026-10-23 | 2026-10-12
2.1.2 | QAS Environment Validation | AWS,RM,VTEC | 0% | 0% | Not Started | 5 days | 2026-10-26 | 2026-10-30
2.1.3 | Security / Network / VPN Configuration | AWS,RM,VTEC | 0% | 0% | Not Started | 5 days | 2026-10-26 | 2026-10-30
2.2 | Development/Configuration/UT/SIT | VTEC | 2.712% | 2.472% | Late | 145 days | 2026-08-11 | 2027-03-01
2.2.1 | BA01 – KeyDataStructure | VTEC | 0% | 0% | Not Started | 104 days | 2026-09-01 | 2027-01-22
2.2.1.1 | Development | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.1.2 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.1.3 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.1.4 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.2 | BA02 – HQ & Reporting | VTEC | 0% | 0% | Not Started | 104 days | 2026-09-01 | 2027-01-22
2.2.2.1 | Development | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.2.2 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.2.3 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.2.4 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.3 | BA03 – CRM & Promotion | VTEC | 3.75% | 3.75% | On Schedule | 70 days | 2026-10-19 | 2027-01-22
2.2.3.1 | Development | VTEC | 15% | 15% | On Schedule | 25 days | 2026-10-19 | 2026-11-20
2.2.3.2 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.3.3 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.3.4 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.4 | BA04 - Payment & Blueplus | VTEC | 8.772% | 7.333% | Late | 75 days | 2026-10-12 | 2027-01-22
2.2.4.1 | Sbox Env Preparation (Blueplus) | RM,VTEC | 26.32% | 22% | Late | 15 days | 2026-10-12 | 2026-10-30
2.2.4.2 | Sbox Env Preparation (K-Bank) | RM,VTEC | 26.32% | 22% | Late | 15 days | 2026-10-12 | 2026-10-30
2.2.4.3 | Development | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.4.4 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.4.5 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.4.6 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.5 | BA05 – Store & Front Operation | VTEC | 3.75% | 3.75% | On Schedule | 104 days | 2026-09-01 | 2027-01-22
2.2.5.1 | Development | VTEC | 15% | 15% | On Schedule | 25 days | 2026-10-19 | 2026-11-20
2.2.5.2 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.5.3 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.5.4 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.6 | BA06 - Store Back Operation & Inventory Management | VTEC | 0% | 0% | Not Started | 104 days | 2026-09-01 | 2027-01-22
2.2.6.2 | Development | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.6.3 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.6.4 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.6.5 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.7 | BA07- Branch Ordering & HQ Procurement Integration | VTEC | 0% | 0% | Not Started | 104 days | 2026-09-01 | 2027-01-22
2.2.7.1 | Sbox Env Preparation (E-Invoice) | RM,VTEC | 0% | 0% | Not Started | 10 days | 2026-10-26 | 2026-11-06
2.2.7.2 | Development | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.7.3 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.7.4 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.7.5 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.2.8 | BA08- E-Tax Integration via IES | VTEC | 0% | 0% | Not Started | 104 days | 2026-09-01 | 2027-01-22
2.2.8.1 | Sbox Env Preparation (E-Tax) | RM,VTEC | 0% | 0% | Not Started | 10 days | 2026-10-26 | 2026-11-06
2.2.8.2 | Development | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.8.3 | UT Execution/Fixing | VTEC | 0% | 0% | Not Started | 25 days | 2026-10-19 | 2026-11-20
2.2.8.4 | SIT Preparation | VTEC | 0% | 0% | Not Started | 21 days | 2026-11-02 | 2026-11-30
2.2.8.5 | SIT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 39 days | 2026-12-01 | 2027-01-22
2.3 | SIT Deliverables Consolidation | RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-01-25 | 2027-01-29
2.3.1 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 3 days | 2027-01-25 | 2027-01-27
2.3.2 | Sign-off | RM | 0% | 0% | Not Started | 2 days | 2027-01-28 | 2027-01-29
2.4 | UAT Plan | RM,VTEC | 0% | 0% | Not Started | 11 days | 2026-12-21 | 2027-01-04
2.4.1 | Preparation | VTEC | 0% | 0% | Not Started | 3 days | 2026-12-21 | 2026-12-23
2.4.2 | Review | RM | 0% | 0% | Not Started | 5 days | 2026-12-24 | 2026-12-30
2.4.3 | Revise | VTEC | 0% | 0% | Not Started | 2 days | 2026-12-31 | 2027-01-01
2.4.4 | Finalization | RM | 0% | 0% | Not Started | 1 days | 2027-01-04 | 2027-01-04
2.5 | UAT Environment Preparation | AWS,RM,VTEC | 0% | 0% | Not Started | 11 days | 2027-01-04 | 2027-01-18
2.5.1 | UAT Environment Setup | AWS,RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-01-05 | 2027-01-11
2.5.2 | UAT Environment Validation | AWS,RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-01-12 | 2027-01-18
2.5.3 | Security / Network / VPN Configuration | AWS,RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-01-04 | 2027-01-08
2.6 | UAT Test Case/Script | RM,VTEC | 0% | 0% | Not Started | 19 days | 2027-01-05 | 2027-01-29
2.6.1 | Preparation | VTEC | 0% | 0% | Not Started | 10 days | 2027-01-05 | 2027-01-18
2.6.2 | Review | RM | 0% | 0% | Not Started | 5 days | 2027-01-19 | 2027-01-25
2.6.3 | Revise | VTEC | 0% | 0% | Not Started | 3 days | 2027-01-26 | 2027-01-28
2.6.4 | Finalization | RM | 0% | 0% | Not Started | 1 days | 2027-01-29 | 2027-01-29
2.7 | UAT Result | RM,VTEC | 0% | 0% | Not Started | 20 days | 2027-02-01 | 2027-02-26
2.7.1 | UAT Execution/Fixing | RM,VTEC | 0% | 0% | Not Started | 20 days | 2027-02-01 | 2027-02-26
2.7.2 | UAT Result Summary | VTEC | 0% | 0% | Not Started | 20 days | 2027-02-01 | 2027-02-26
2.8 | UAT Deliverables Consolidation | RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-03-01 | 2027-03-05
2.8.1 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 3 days | 2027-03-01 | 2027-03-03
2.8.2 | Sign-off | RM | 0% | 0% | Not Started | 2 days | 2027-03-04 | 2027-03-05
2.9 | Design Specification Document Updated (if any) | RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.9.1 | Preparation | VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.9.2 | Review | RM | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.9.3 | Revise | VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.9.4 | Finalization | RM | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.9.5 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.9.6 | Sign-off | RM | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.1 | Technical Specification Document Updated (if any) | RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.10.1 | Preparation | VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.10.2 | Review | RM | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.10.3 | Revise | VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.10.4 | Finalization | RM | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.10.5 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
2.10.6 | Sign-off | RM | 0% | 0% | Not Started | 15 days | 2027-03-01 | 2027-03-19
3 | Milestone3 - Pilot Go-live (30%) | RM,VTEC,VTEC-ROLLOUT | 0% | 0% | Not Started | 108 days | 2027-02-01 | 2027-06-30
3.1 | Training Class Document/User Manual | RM,VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.1.1 | Preparation | VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.1.2 | Review | RM | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.1.3 | Revise | VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.1.4 | Finalization | RM | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.1.5 | Execution | RM,VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2 | Technical Manual | RM,VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2.1 | Preparation | VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2.2 | Review | RM | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2.3 | Revise | VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2.4 | Finalization | RM | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2.5 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.2.6 | Sign-off | RM | 0% | 0% | Not Started | 45 days | 2027-03-01 | 2027-04-30
3.3 | Cutover and Data Migration | RM,VTEC | 0% | 0% | Not Started | 65 days | 2027-02-01 | 2027-04-30
3.3.1 | Cutover Plan | RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.1.1 | Preparation | VTEC | 0% | 0% | Not Started | 5 days | 2027-02-01 | 2027-02-05
3.3.1.2 | Review | RM | 0% | 0% | Not Started | 5 days | 2027-02-08 | 2027-02-12
3.3.1.3 | Revise | VTEC | 0% | 0% | Not Started | 3 days | 2027-02-15 | 2027-02-17
3.3.1.4 | Finalization | RM | 0% | 0% | Not Started | 2 days | 2027-02-18 | 2027-02-19
3.3.2 | PRD Environment Preparation | AWS,RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.2.1 | PRD Environment Setup | AWS,RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.2.2 | PRD Environment Validation | AWS,RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.2.3 | Security / Network / VPN Configuration | AWS,RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.2.4 | Backup & Monitoring Configuration | AWS,RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.2.5 | Infrastructure Readiness Sign-off | RM | 0% | 0% | Not Started | 15 days | 2027-02-01 | 2027-02-19
3.3.3 | Go-Live Readiness Checklist |  | 0% | 0% | Not Started | 15 days | 2027-02-22 | 2027-03-12
3.3.3.1 | Preparation | VTEC | 0% | 0% | Not Started | 5 days | 2027-02-22 | 2027-02-26
3.3.3.2 | Review | RM | 0% | 0% | Not Started | 5 days | 2027-03-01 | 2027-03-05
3.3.3.3 | Revise | VTEC | 0% | 0% | Not Started | 3 days | 2027-03-08 | 2027-03-10
3.3.3.4 | Finalization | RM | 0% | 0% | Not Started | 2 days | 2027-03-11 | 2027-03-12
3.3.4 | Cutover Execution & Report | RM,VTEC | 0% | 0% | Not Started | 30 days | 2027-03-15 | 2027-04-23
3.3.4.1 | Cutover Preparation | RM,VTEC | 0% | 0% | Not Started | 10 days | 2027-03-15 | 2027-03-26
3.3.4.2 | Cutover Execution | RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-03-29 | 2027-04-16
3.3.4.3 | Cutover Report Prep. | VTEC | 0% | 0% | Not Started | 5 days | 2027-04-19 | 2027-04-23
3.3.5 | Cutover Deliverables Consolidation | RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-04-26 | 2027-04-30
3.3.5.1 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 3 days | 2027-04-26 | 2027-04-28
3.3.5.2 | Sign-off | RM | 0% | 0% | Not Started | 2 days | 2027-04-29 | 2027-04-30
3.4 | Pilot Site Implementation | RM,VTEC,VTEC-ROLLOUT | 0% | 0% | Not Started | 29 days | 2027-04-05 | 2027-05-13
3.4.1 | Pilot Site Plan | RM,VTEC | 0% | 0% | Not Started | 15 days | 2027-04-05 | 2027-04-23
3.4.1.1 | Preparation | VTEC | 0% | 0% | Not Started | 5 days | 2027-04-05 | 2027-04-09
3.4.1.2 | Review | RM | 0% | 0% | Not Started | 3 days | 2027-04-12 | 2027-04-14
3.4.1.3 | Revise | VTEC | 0% | 0% | Not Started | 5 days | 2027-04-15 | 2027-04-21
3.4.1.4 | Finalization | RM | 0% | 0% | Not Started | 2 days | 2027-04-22 | 2027-04-23
3.4.2 | Pilot Site Execution | RM,VTEC,VTEC-ROLLOUT | 0% | 0% | Not Started | 9 days | 2027-04-26 | 2027-05-06
3.4.2.1 | Pilot Site Preparation | RM,VTEC | 0% | 0% | Not Started | 5 days | 2027-04-26 | 2027-04-30
3.4.2.2 | 5-Stores Remote Update | VTEC | 0% | 0% | Not Started | 2 days | 2027-05-03 | 2027-05-04
3.4.2.3 | 5-Stores Remote Update | VTEC-ROLLOUT | 0% | 0% | Not Started | 2 days | 2027-05-05 | 2027-05-06
3.4.3 | Pilot Site Deliverables Consolidation | RM,VTEC | 0% | 0% | Not Started | 9 days | 2027-05-03 | 2027-05-13
3.4.3.1 | Sign-off Preparation | VTEC | 0% | 0% | Not Started | 5 days | 2027-05-07 | 2027-05-13
3.4.3.2 | Sign-off | RM | 0% | 0% | Not Started | 5 days | 2027-05-03 | 2027-05-07
3.5 | Pilot Monitoring and Hypercare (2 Months) | RM,VTEC | 0% | 0% | Not Started | 43 days | 2027-05-03 | 2027-06-30
4 | Milestone4 - Massive Rollout (30%) | VTEC-ROLLOUT | 0% | 0% | Not Started | 66 days | 2027-07-01 | 2027-09-30
Formulas:
Duration = NETWORKDAYS([Start], [Finish]) & " days"
Note on C93: ====== ID#AAAB7Ghitcs NipapornJ (2026-05-25 02:40:45) - Hardware, Security and Network Specifications - Architecture and System Landscape (As is) - Architecture and System Landscape (To be)
Note on C194: ====== ID#AAAB7Ghitcw NipapornJ (2026-05-25 02:40:45) - System and Network Architect Manual - Technical Manual - Troubleshoot and Operation Manual
Note on C201: ====== ID#AAAB7Ghitck NipapornJ (2026-05-25 02:40:45) - Cutover Plan - Cutover Report - Go-live Readiness Check List
Note on C225: ====== ID#AAAB7Ghitco NipapornJ (2026-05-25 02:40:45) - Pilot Site Plan (10 stores) - Pilot Site Report - 5 stores done by VTEC - 5 stores done by MSI
Note on C233: ====== ID#AAAB7Ghitc0 NipapornJ (2026-05-25 02:40:45) on-the-job training to MSI